## 📋 Project Overview
TELCO X — SERVICE AVAILABILITY PROTOTYPE
Project Plan ¦ RMIT AI Workshop ¦ Team 3
PROJECT DETAILS
Project Name | Telco X Service Availability Prototype | Project Duration | 2 hours (09:00 – 11:00)
Project Manager | Ranjith Rufus | Workshop Date | RMIT AI Workshop – Day 2
Product Manager | Sarah Campbell | Methodology | Agile – 2 Sprints
Business Analyst | Ravneet Kaur | Demo at Midpoint | Sprint 1 Review @ 10:00
UX Designer | Mahesh Yeganathan | Sprint Length | 1 hour each
Engineer | Warren Bailey | Repo | telco-x-starter (GitHub)
Test Engineer | Mayuri Reddy | Status | Planning
PROJECT OBJECTIVE
Build a responsive 3-page web app (Telco X Service Availability Prototype) that allows users to search addresses, view subscriber status, and explore available products/providers. Built on the telco-x-starter, using AI-assisted development across the full SDLC within a 2-hour workshop sprint.
DEFINITION OF DONE (Assessment Criteria)
Criterion | Description | Sprint Target | Status
DoD 1 | All ten addresses can be searched or selected | Sprint 1 | Not Started
DoD 2 | Unknown address shows a helpful error | Sprint 1 | Not Started
DoD 3 | Result page shows the right address + map pin | Sprint 1 | Not Started
DoD 4 | Active shows subscriber, network & service details | Sprint 1 | Not Started
DoD 5 | Non-active shows valid product choices | Sprint 1 | Not Started
DoD 6 | Detail and provider views open correctly | Sprint 2 | Not Started
DoD 7 | Provider names and count match the data exactly | Sprint 2 | Not Started
DoD 8 | Back navigation keeps the selected address | Sprint 2 | Not Started
DoD 9 | Works on laptop and mobile, clearly labelled | Sprint 2 | Not Started
DoD 10 | Demo: one active journey (Carlton) + one non-active (Williamstown) | Sprint 2 | Not Started

## 📅 Schedule Plan
SCHEDULE PLAN — TELCO X PROJECT
Total Duration: 2 Hours ¦ Sprint 1: 09:00–10:00 ¦ Mid-Point Demo: 10:00 ¦ Sprint 2: 10:00–11:00
# | Phase / Task | Description | Start | End | Owner(s) | DoD Ref | Status
SPRINT 1 — BUILD CORE
1.1 | Read & Align | Assign roles, agree demo addresses (Carlton/Williamstown), agree 404 rule for non-active subscriber requests | 09:00 | 09:15 | All Team | — | Not Started
1.2 | Plan & Design | PM one-page brief; BA – Given/When/Then ACs; UX – sketch pages 2&3 in Claude Design; Engineer – Plan Mode route mapping; Tester – path matrix draft | 09:15 | 09:35 | Sarah, Ravneet, Mahesh, Warren, Mayuri | DoD 3–7 | Not Started
1.3 | Build Core – API Endpoints | Implement 6 TODO endpoints in order: technology→products→subscriber (isActive guard!)→network→service→providers. Run npm test after each. | 09:35 | 10:30 | Warren | DoD 1,2,4,5,7 | Not Started
1.4 | Build Page 2 – Result | Fetch location, branch on connection_status, render active vs non-active paths. UX commit design/result.html and raise design-handoff Issue. | 09:35 | 10:30 | Warren, Mahesh | DoD 3,4,5 | Not Started
1.5 | SPRINT 1 DEMO / REVIEW | ⭐ MID-POINT DEMO — Show working Page 2 with both active and non-active paths. Team review & retrospective. | 10:00 | 10:10 | Ranjith (PM) | DoD 3,4,5 | Not Started
SPRINT 2 — BUILD DETAIL, TEST & POLISH
2.1 | Build Page 3 – Details Mode | details.js two modes from ?mode= URL param. Details mode: full subscriber view (Tools 4,5,6). UX commit design/details.html. | 10:10 | 10:30 | Warren, Mahesh | DoD 4,6 | Not Started
2.2 | Build Page 3 – Providers Mode | providers mode: provider list from Tool 7 (?tech= param, encodeURIComponent). Wire Back button to history.back(). | 10:10 | 10:30 | Warren | DoD 6,7,8 | Not Started
2.3 | Test – API & Path Matrix | Activate skipped tests in tests/api.test.js. Run npm test — all 31 must pass. Check non-active data leaks, upgrade card logic, Fixed Wireless provider count, mobile 375px. | 10:30 | 10:50 | Mayuri | DoD 1–9 | Not Started
2.4 | Defect Fix | Fix blocker defects only — leave minor for debrief. PM to triage. | 10:50 | 10:55 | Warren, Mayuri, Ranjith | All DoD | Not Started
2.5 | Polish & Demo Rehearse | Rehearse two journeys: Carlton (active) → Williamstown (never). Name two 🔴 human moments. PM to tell the project story. | 10:55 | 11:00 | All Team | DoD 10 | Not Started
2.6 | FINAL DEMO | ⭐ FINAL SHOWCASE — 5 min, running app, no slides. Active journey + non-active journey + one human call. | 11:00 | 11:05 | Ranjith (PM) | DoD 10 | Not Started

## 📊 Schedule Tracking
SCHEDULE TRACKING — VISUAL GANTT (2-Hour Sprint)
# | Task | Owner | 09:00 | 09:15 | 09:30 | 09:45 | 10:00 | 10:15 | 10:30 | 10:45 | 11:00
── SPRINT 1 ──
1.1 | Read & Align | All | ▓
1.2 | Plan & Design | Sarah/Ravneet/Mahesh/Warren/Mayuri |  | ▓
1.3 | Build Core – APIs | Warren |  |  | ▓ | ▓ | ▓ | ▓
1.4 | Build Page 2 | Warren/Mahesh |  |  | ▓ | ▓ | ▓ | ▓
1.5 | ⭐ MID DEMO / Review | Ranjith |  |  |  |  | ▓
── SPRINT 2 ──
2.1 | Build Page 3 Details | Warren/Mahesh |  |  |  |  | ▓ | ▓
2.2 | Build Page 3 Providers | Warren |  |  |  |  | ▓ | ▓
2.3 | Test – All 31 Tests | Mayuri | [6 empty] | ▓
2.4 | Defect Fix | Warren/Mayuri | [7 empty] | ▓
2.5 | Polish & Rehearse | All | [7 empty] | ▓
2.6 | ⭐ FINAL DEMO | Ranjith | [8 empty] | ▓

## ✅ Action Tracker
ACTION TRACKER — TELCO X PROJECT
ID | Action | Owner | Raised | Due | Priority | Notes | Status
A-01 | Fork telco-x-starter repo and confirm all team members have access | Warren | Sprint 1 Start | 09:15 | High | GitHub setup prerequisite | Open
A-02 | Agree 404 vs 403 response for non-active subscriber requests | Ranjith / Ravneet | Sprint 1 Start | 09:15 | High | 🔴 Human Decision required | Open
A-03 | Choose 2 demo addresses: Carlton (active) + Williamstown (never) | Sarah | Sprint 1 Start | 09:15 | High | Confirm from Tool 1 data | Open
A-04 | BA: Write Given/When/Then ACs for all 6 endpoints + sign off | Ravneet | 09:15 | 09:35 | High | Must be signed off by PM before build starts | Open
A-05 | UX: Sketch Page 2 & 3 in Claude Design; commit design/result.html | Mahesh | 09:15 | 09:45 | High | First cut requirements already done | Open
A-06 | UX: Commit design/details.html + raise design-handoff Issue | Mahesh | 09:35 | 10:15 | Medium |  | Open
A-07 | Engineer: Plan Mode — map all 6 TODO endpoints before coding | Warren | 09:15 | 09:35 | High | Shift+Tab in Claude Code | Open
A-08 | Implement endpoint: GET /api/locations/:id/technology | Warren | 09:35 | 09:50 | High | Order: technology first | Open
A-09 | Implement endpoint: GET /api/technology/:tech/products | Warren | 09:50 | 10:00 | High |  | Open
A-10 | Implement endpoint: GET /api/locations/:id/subscriber (isActive guard!) | Warren | 10:00 | 10:10 | High | isActive() guard MUST run before getSubscriber/getNetwork/getService | Open
A-11 | Implement endpoints: network, service, providers | Warren | 10:10 | 10:25 | High | Run npm test after each | Open
A-12 | Build Page 2 (result.js) — both active and non-active paths | Warren | 09:35 | 10:30 | High |  | Open
A-13 | ⭐ MID-POINT DEMO: Present Sprint 1 output to team | Ranjith | Sprint 1 End | 10:00 | High | Show both active + non-active paths on Page 2 | Open
A-14 | Build Page 3 details mode — Tools 4, 5, 6 | Warren | 10:10 | 10:30 | High |  | Open
A-15 | Build Page 3 providers mode — Tool 7, encodeURIComponent for tech param | Warren | 10:10 | 10:30 | High | encodeURIComponent not + encoding | Open
A-16 | Wire Back button to history.back() — do NOT hard-code URL | Warren | 10:25 | 10:35 | Medium | DoD 8 | Open
A-17 | Tester: Activate skipped tests in tests/api.test.js | Mayuri | 10:30 | 10:45 | High | All 31 tests must pass | Open
A-18 | Tester: Walk full path matrix in browser; verify no data leaks | Mayuri | 10:30 | 10:50 | High | Check LOC-005 to LOC-010 hide subscriber data | Open
A-19 | Tester: Verify upgrade card logic (LOC-001/004=false, LOC-002/003=true) | Mayuri | 10:30 | 10:50 | High | DoD 4 | Open
A-20 | Tester: Verify Fixed Wireless shows exactly 2 provider names | Mayuri | 10:30 | 10:50 | High | DoD 7 | Open
A-21 | Tester: Check mobile layout at 375px width | Mayuri | 10:30 | 10:50 | Medium | DoD 9 | Open
A-22 | Fix all blocker defects; triage with PM | Warren / Ranjith | 10:50 | 10:55 | High | Minor issues left for debrief | Open
A-23 | Rehearse final demo — 2 journeys: Carlton → Williamstown | All Team | 10:55 | 11:00 | High |  | Open
A-24 | Name two 🔴 Human Moments (404 decision + merge approval) | Ranjith | 10:55 | 11:00 | Medium | Required for showcase story | Open
A-25 | ⭐ FINAL DEMO — 5 min, running app, no slides | Ranjith | 11:00 | 11:05 | High | Active journey + non-active journey + 1 human call | Open

## ⚠️ Risk Register
RISK REGISTER — TELCO X PROJECT
🔴 High 🟡 Medium 🟢 Low
ID | Risk Description | Category | Likelihood | Impact | Rating | Mitigation | Owner | Status
R-01 | Schedule Risk: 2-hour window is extremely tight for full SDLC | Schedule | High | High | 🔴 High | Strict timeboxing per phase; PM to call time; cut scope before quality; use AI to accelerate all coding & testing | Ranjith | Open
R-02 | AI Over-Reliance: Team accepts AI output without review, ships defects | AI Usage | High | High | 🔴 High | Enforce 🔴 Human Decision gates (merge approval, 404 rule); PM to prompt team to review every AI draft before accepting | Ranjith | Open
R-03 | Team AI Literacy: Some members unfamiliar with Claude Code / Claude Design | Knowledge | High | Medium | 🔴 High | PM to pair experienced with less-experienced; use starter prompts on challenge page; 5-min tool intro at Read & Align | Ranjith / Sarah | Open
R-04 | isActive Guard Missing: Subscriber data leaks to non-active addresses | Technical | Medium | High | 🔴 High | BA to include isActive guard in ACs; Tester to explicitly check LOC-005–010 in path matrix; code review before merge | Ravneet / Mayuri | Open
R-05 | encodeURIComponent Bug: Fixed Wireless providers returns 0 due to + encoding | Technical | Medium | High | 🟡 Medium | Engineer checklist includes encodeURIComponent; Tester to verify Fixed Wireless shows exactly 2 providers | Warren / Mayuri | Open
R-06 | npm test Failures: Tests not passing blocks Polish phase | Technical | Medium | High | 🟡 Medium | Run npm test after every endpoint; never move to next endpoint with failing tests; 31 tests must be green before Polish | Warren | Open
R-07 | Design Handoff Delay: UX sketches not available before build starts | Schedule | Medium | Medium | 🟡 Medium | Mahesh to commit design/result.html by 09:45 at latest; Engineer can start with semantic HTML and apply styles after | Mahesh | Open
R-08 | Scope Creep: Team adds features not in DoD criteria | Scope | Low | Medium | 🟡 Medium | PM to hold firm on the 10 DoD criteria; any additions must be explicitly agreed and time-checked; fix blockers only in Polish | Ranjith | Open
R-09 | Upgrade Card Logic Error: Card shown when upgrade_eligible=false | Technical | Medium | Medium | 🟡 Medium | BA to specify exact condition in ACs: upgrade_eligible===true; Tester to verify LOC-001 and LOC-004 hide card | Ravneet / Mayuri | Open
R-10 | Demo Failure: App not demo-ready at 11:00 | Schedule | Low | High | 🟡 Medium | Mid-point demo at 10:00 acts as insurance; rehearse two journeys at 10:55; fix blockers only — leave cosmetics | Ranjith | Open
R-11 | AI Hallucination in Code: Claude generates wrong API routes or data access patterns | AI Usage | Medium | High | 🔴 High | Always reference CLAUDE.md guardrails; never read /data JSON directly — always use lib/data.js getters; test after each endpoint | Warren | Open
R-12 | Mobile Responsiveness: App not usable at 375px (DoD 9) | Technical | Low | Medium | 🟢 Low | Tester to check 375px width during test phase; UX to ensure responsive design in sketches from the start | Mayuri / Mahesh | Open

## 🔗 Dependencies
DEPENDENCY TRACKER — TELCO X PROJECT
ID | Predecessor Task | Successor Task (Blocked) | Owner(s) | Due | Notes | Status
D-01 | Read & Align complete (A-01 to A-03) | All planning and build tasks | Ranjith | 09:15 | Nothing starts until roles, demo addresses and 404 rule are agreed | Open
D-02 | BA ACs written & signed off (A-04) | Build Core (A-07 to A-12) | Ravneet → Warren | 09:35 | Engineer must not start coding without agreed ACs | Open
D-03 | Engineer Plan Mode — route mapping (A-07) | All 6 endpoint implementations (A-08 to A-11) | Warren | 09:35 | Cannot implement endpoints without knowing the route plan | Open
D-04 | technology endpoint done (A-08) | products endpoint (A-09) | Warren | 09:50 | Tool 2 (technology) drives product selection via Tool 3 | Open
D-05 | subscriber endpoint done with isActive guard (A-10) | network & service endpoints (A-11) | Warren | 10:10 | Network/Service data only available for active locations | Open
D-06 | All 6 endpoints 200 OK + npm test green | Build Page 2 (A-12) | Warren | 10:30 | Page 2 must fetch real API responses — cannot be mocked | Open
D-07 | UX design/result.html committed (A-05) | Page 2 styling | Mahesh → Warren | 09:45 | Styling can follow semantic build but must be applied before demo | Open
D-08 | Page 2 both paths working (A-12) | ⭐ Mid-Point Demo (A-13) | Warren → Ranjith | 10:00 | Demo requires at least Page 2 functional | Open
D-09 | Mid-Point Demo & Sprint 1 Review (A-13) | Sprint 2 tasks (A-14 to A-16) | Ranjith → All | 10:10 | Sprint 2 scope confirmed after demo feedback | Open
D-10 | subscriber endpoint (active guard) done (A-10) | Page 3 details mode (A-14) | Warren | 10:30 | Tools 4, 5, 6 all require active guard | Open
D-11 | providers endpoint done (A-11) | Page 3 providers mode (A-15) | Warren | 10:30 | Provider list from Tool 7 drives providers mode | Open
D-12 | UX design/details.html committed (A-06) | Page 3 styling | Mahesh → Warren | 10:15 |  | Open
D-13 | All 6 endpoints + Pages 2 & 3 complete | Test phase — all 31 tests (A-17 to A-21) | Warren → Mayuri | 10:30 | Testing requires all endpoints and pages to be built | Open
D-14 | All 31 tests pass (A-17 to A-21) | Polish & Demo Rehearse (A-23) | Mayuri → Ranjith | 10:50 | No polish until all tests green — blockers fixed first | Open
D-15 | Defect fix complete (A-22) | Final Demo (A-25) | Warren → Ranjith | 11:00 | Demo must run end-to-end with no blockers | Open

## 🐛 Issue Tracker
ISSUE TRACKER — TELCO X PROJECT
ID | Issue Description | Category | Severity | Reported By | Phase Found | Resolution / Fix | Owner | Status
I-01 | Endpoint returns 501 (not yet implemented) | Technical | Blocker | Warren / Mayuri | Build Core | Open server.js, find TODO stub, implement using lib/data.js getter per hint comment | Warren | Pre-identified
I-02 | Page 2 shows nothing — ?id= param missing from URL | Technical | Blocker | Warren | Build Core | Check result.js reads params.get('id') from URL search params | Warren | Pre-identified
I-03 | Fixed Wireless shows 0 providers — + encoding bug | Technical | High | Mayuri | Test | Change fetch call to use encodeURIComponent(tech) — not manual + replacement | Warren | Pre-identified
I-04 | Subscriber data leaks for non-active address | Technical | Blocker | Mayuri | Test | Add isActive() guard before any call to getSubscriber/getNetwork/getService | Warren | Pre-identified
I-05 | Upgrade card always shows or never shows | Technical | High | Mayuri | Test | Check condition: subscriber.upgrade_eligible===true. LOC-001/004=false; LOC-002/003=true | Warren | Pre-identified
I-06 | Back button goes to Page 1 instead of preserving address | Technical | Medium | Mayuri | Test | Replace location.href with history.back() in back button click handler | Warren | Pre-identified
I-07 | Mobile layout broken at 375px | UX | Medium | Mayuri | Test | Mayuri to log; UX (Mahesh) and Engineer to fix responsive CSS | Mahesh / Warren | Pre-identified
I-08 | [PLACEHOLDER] New issue to be raised during build | TBD | TBD | TBD | TBD |  | TBD | Open
I-09 | [PLACEHOLDER] New issue to be raised during build | TBD | TBD | TBD | TBD |  | TBD | Open
I-10 | [PLACEHOLDER] New issue to be raised during build | TBD | TBD | TBD | TBD |  | TBD | Open

## 👥 Team & Roles
TEAM & ROLES — TELCO X PROJECT
Name | Role | Key Responsibilities | Sprint Assignments
Ranjith Rufus | Project Manager | Remove blockers; timebox phases; call checkpoints; triage defects; facilitate mid-point and final demos; name 🔴 Human Decision moments; tell the project story | Sprint 1: Read & Align, Mid-Demo ¦ Sprint 2: Defect Triage, Demo Rehearsal, Final Demo
Sarah Campbell | Product Manager | Define scope and priorities; write one-page brief for first slice (Stage/Task/Rules); propose build order for demoable slice by halfway; flag single riskiest item; own the showcase narrative | Sprint 1: Plan phase — one-page brief + build order
Ravneet Kaur | Business Analyst | Map each acceptance criterion to tool(s) and screen element; write Given/When/Then ACs for all 6 endpoints; flag any criterion data cannot satisfy; sign off ACs before build starts | Sprint 1: Plan phase — ACs + business rules
Mahesh Yeganathan | UX Designer | Design system, prototype & accessibility; sketch Pages 2 & 3 in Claude Design; commit design/result.html (by 09:45) and design/details.html (by 10:15); raise design-handoff Issues; review for contrast, focus order, label clarity | Sprint 1: design/result.html ¦ Sprint 2: design/details.html, accessibility review
Warren Bailey | Engineer | Implement all 6 TODO endpoints in server.js (in order: technology → products → subscriber → network → service → providers); build Pages 2 & 3; use lib/data.js getters ONLY; run npm test after each endpoint; fix blocker defects | Sprint 1: API endpoints + Page 2 ¦ Sprint 2: Page 3 (both modes) + defect fixes
Mayuri Reddy | Test Engineer | Draft path matrix on paper during Plan; activate skipped tests in tests/api.test.js; run npm test — all 31 must pass; walk path matrix in browser; verify non-active data isolation, upgrade card logic, Fixed Wireless provider count, mobile 375px; write defect list | Sprint 1: Path matrix draft ¦ Sprint 2: Full test execution + defect reporting
AI USAGE FRAMEWORK (Three-Tier)
🔴 Human Decision | You decide — NO AI | Approvals, trade-offs, what 'done' means, the merge. 404 vs 403 rule. Final demo narrative.
🟡 AI Assist | Claude drafts; you review & approve | Requirements, designs, test plans, code review comments, PR descriptions. MUST be reviewed before it counts.
🟢 AI Automate | Claude runs it; you monitor | Scaffolding, boilerplate, test generation, endpoint stubs, CSS. Monitor output quality.